## Sheet1
Application Pre-Flight Matrix
www.tilsontech.com/broadband-funding
Task | Ownership | Target Completion Date | Status | Additional Notes
Internal Kickoff meeting | John Smith | 2021-04-28 | Complete
SF-424 Grants.gov Form | Arthur Curry | 2021-05-04 | In Progress
Executive Summary | Kate Kane | 2021-05-04 | In Progress
Scoring Criteria Documentation | Arthur Curry | 2021-05-04 | In Progress
Scope of Work | Kate Kane | 2021-05-04 | In Progress
Financial Information and Sustainability | Kara Zor-El | 2021-05-18 | In Progress
Statement of Experience | Kate Kane | 2021-05-18 | Complete
Funding Commitments from All Sources | Peter Parker | 2021-05-18 | In Progress | cc Clark Kent
Telecommunications System Plan | Kate Kane | 2021-06-01 | In Progress
Compliance with Federal Statutes | Arthur Curry | 2021-06-01 | Complete
Non-Duplication of Services Form | Kara Zor-El | 2021-06-01 | Complete
Mock Application Review | John Smith | 2021-06-14 | Not Started
SAM.gov Certifications and Representations | Arthur Curry | 2021-06-14 | In Progress
Environmental Review Requirements | Arthur Curry | 2021-06-14 | Not Started
Evidence of Legal Authority and Existence with CAGE code. | Arthur Curry | 2021-06-14 | Not Started
Federal Debt Certification | Peter Parker | 2021-06-14 | Not Started
Documentation of Consultation with USDA State Director | John Smith | 2021-06-14 | Not Started
Supplemental Information | Kate Kane | 2021-06-14 | Not Started
Team Review | John Smith | 2021-06-21 | Not Started
Submit via Portal | John Smith | 2021-06-28 | Not Started | by 2pm, one via portal and one via mail